## Slide 1: CSEN 285 Case Study #1
Development Plan based on the requirements document given.
Chirag, Divya, Sam (Yu Cheng Wu), Siddhant

## Slide 2: Introduction
The company has decided to upgrade the current system in use for tracking sales and records. The present system cannot cope with the increasing numbers related to sales and products. The new system will meet the following expected requirements:
Maintain records for around 40 products.
Accommodate details of 200 salespersons, around 30,00 customers, and the various operations involving them.
System accessible to warehouse clerks, sales reports by Tony.
Compatible with IBM computers.
Quick response times.
Generate reports of monthly sale totals, products sold/returned, and sales reports per salesperson (available to the individual).

## Slide 3: Project Organization
Tony Carrasco:
Main project supervisor including approval for stages of development, communicator between project participants and upper management.
Alan Scott (VP of R&D):
Final approval for project development.
Warehouse Clerks:
Users of the system could be recruited to conduct beta testing of the system before it’s rolled out.

## Slide 4: Project Organization (cont.)
Consultants:
Assist in test planning, identify areas of improvement in the test process, and develop a systems test plan.
Testers (Joe Blank, Mike Brosne, Jon Underwood):
Conduct the testing for the new sales system including unit testing, integration testing, system testing, and regression testing if possible.
Development Team
Develop the system including all the necessary components, functionality, and user interface.

## Slide 5: Risk Analysis & Mitigation Strategies
Shortage of time for testing and correction:
With the New Year deadline, employees’ holiday schedules could lead to delays in the final release.
Mitigation Strategies: Early test planning, Hiring external support, Parallel testing, Developers involvement in testing.
Regression Testing:
Integration of the new system into our current internal software system should be tested independently of the main.
Mitigation Strategies:
Phased Integration, Isolated Testing Environment.

## Slide 6: Risk Analysis & Mitigation Strategies
Compatibility and Configuration Management Issues:
The IBM PCs each may have different configurations in terms of processors, operating systems, and power. Issues might arise with the Sales System working smoothly on the PCs.
Mitigation Strategies:
Configuration Management Tools, Virtualization Solutions.
Data Migration:
Potential data integrity issues can arise when migrating the data from the old system to the new Sales system.
Mitigation Strategies:
Data Validation/Cleansing, Post-Migration Verification.

## Slide 7: Risk Analysis & Mitigation Strategies
Staff Availability:
With the target date for the new system expected as the end of Dec 2024, staff availability will be a major issue considering the holiday season. Most employees may offer availability on different dates which could delay the readiness of the system.
Mitigation Strategies:
Staff will provide their PTO schedule by October 15 for management to plan ahead.
Staff Readiness:
Potential customer/staff complaints should be handled from day 1.
Mitigation Strategies:
Staff training on Beta version.

## Slide 8: HW and SW Resources
HW:
IBM Mainframe, IBM PCs, and dedicated systems for testing.
SW:
IDE to program system, version control, testing tools/framework, database management system to handle sales information, and software to generate sales reports.

## Slide 9: Work Breakdown Structure
- Requirements analysis
Req document -> Req Review minutes-> Start RVM.
Deliverable: Requirements doc draft completed.
- Software design
Design document ->Design document minutes -> Update RVM.
Deliverable: Finalizing system design document.

## Slide 10: Work Breakdown Structure (cont.)
- Software Development
Code -> Code Review Minutes ->Update RVM -> Unit test results.
Deliverable: A fully functional sales system.
-Software Testing
Test plan -> Test cases -> Test plan review minutes ->Finalize RVM
->Defect Reports.
Deliverable: A fully tested system ready for deployment.
-Maintenance

## Slide 11: Project Schedule
PHASE | DURATION | START DATE | END DATE
Requirement Analysis | 2 Weeks | August 15 2024 | August 30 2024
System Design | 3 Weeks | September 03 2024 | September 22 2024
System Development | 6 Weeks | September 23 2024 | October 31 2024
System Testing | 7 Weeks | November 01 2024 | December 20 2024
Deployment | 1 Week | December 23 2024 | December 28 2024
Maintenance |  | From 2025. | 

## Slide 12: Measurements
Weekly Review Meetings-
Conduct weekly meetings to review progress, identify potential improvements, and rectify issues. Highlight and plan through crucial dependencies and resource allocation to prevent conflicts in the future.
Review & Evaluation at each Milestone-
Review the status of the project after each milestone (Ex: delivery of requirement document, delivery of design document).

## Slide 13: Measurements
In-process Metrics-
Resource Availability- Helps track the availability of resources. This can help in being a step ahead in terms of resource allocation and utilization. Further, it helps ensure adequate staffing at all times.
Percentage of requirements completed- Identify how much of the project scope has been implemented. This can help identify potential delays.

## Slide 14: Measurements
Efficiency in utilizing resources-
Tracking efficiency of resource utilization can help establish better roadmap during system development.
Deliverables-
Code and other documentations.
Status Reports-
Reports summarizing progress, challenges, and next steps.